## Slide 1: Test Plan Document Project Name : “Kushi Travels” Web Application
Prepared By: S.Prashanth
Date: 12/06/24

## Slide 2: Table of Contents
Overview ……………………………………………………………………………………………………………… 2
Scope ……………………………………………………………………………………………………………………. 3
Inclusion …………………………………………………………………………………………………………… 3
Test Environments ……………………………………………………………………………………………. 3
Exclusions ………………………………………………………………………………………………………… 3
Roles/Responsibilities ………………………………………………………………………………………….. 4
Test Schedule ………………………………………………………………………………………………………. 5
Test Deliverables …………………………………………………………………………………………………. 6
Entry and Exit Criteria …………………………………………………………………………………………. 7
Tools ……………………………………………………………………………………………………………………..8
Risks and Mitigations …………………………………………………………………………………………. 9
Approvals ……………………………………………………………………………………………………………. 10

## Slide 3: Overview
As part of the project, “Kushi Travels” has asked Masai to test few functionalities of ‘https://kushitravels.com/index.php’ web application.
This document serves as high level test planning document with details on the scope of the project, test strategy, test schedule and resource requirements, test deliverables and schedule.

## Slide 4
Scope
The scope of the project includes testing the following features of ‘https://kushitravels.com/index.php’ web application
Inclusions
Register
Login and Logout Feature
Home Page
Type of Travel
Pick-up City, location
Pick-up Date and time
Drop-off date and time
Vehicle type
Confirmation
logout
Test Environments
Windows 11 - Chrome, Firefox and Edge
Android Mobile OS – Chrome
Exclusions
All the features except that are mentioned under ‘Inclusions’
Test Automation

## Slide 5: Roles/Responsibilities
Name | Role | Responsibilities
S.Prashanth | Test Engineer | Understand customer requirement Write Test scenarios & Test cases Execute the Test cases. Report defects
 |  | Conduct Functional, Integration Execute the Test cases Reported the defects

## Slide 6: Test Schedule Following is the test schedule planned for the project:
Task | Time Duration
Creating Test Plan | May 20th, 2024 to May 23rd, 2024
Test case Creation | May 24th, 2024 to June 4th, 2024
Test case Execution | June 5th, 2024 to June 12th, 2024
Summary Report Submission | June 13th, 2024

## Slide 7: Test Deliverables The following are to be delivered to the client:
Deliverables | Description | Responsible Owner | Target Completion Date
Test Plan | Details on the scope of the Project, test strategy, test schedule, resource requirements, test deliverables and schedule | Prashanth | May 20th, 2024 to May 23rd, 2024
Functional Test Cases | Test Cases created for the scope defined | Prashanth | May 24th, 2024 to June 4th, 2024
Defect Reports | Detailed description of the defects identified along with screenshots and steps to reproduced daily basis. | Prashanth | June 5th, 2024 to June 12th, 2024
Summary Reports | Summary Reports – Bug by Bug#, Bugs by Functional Area and Bugs by Priority | Prashanth | June 13th, 2024

## Slide 8
Entry and Exit Criteria
The below are the entry and exit criteria for every phase of Software Testing Life Cycle
Requirement Analysis
Entry Criteria:
Once the testing team receives the Requirements Documents or project details about the Project which serves as the foundation for the testing process, providing the testing team with insights into what needs to be tested and how the software should behave.
Exit Criteria:
The testing team should thoroughly explore and understand each requirement listed in the documents or project details.
Any doubts or uncertainties regarding the requirements should be addressed and clarified to ensure that the testing team has a clear understanding of what needs to be tested and how it should behave.
Test Planning
Entry Criteria:
Testable Requirements derived from the given Requirements Documents or Project details
Any doubts or uncertainties regarding the requirements should be addressed and clarified to ensure that the testing team has a clear understanding of what needs to be tested and how it should behave.
Exit Criteria:
Test Plan document which includes the Test Strategy, which provides a high-level overview of how testing will be conducted. is signed-off by the Client (Flipkart)

## Slide 9
Test Designing
Entry Criteria:
The Test Plan document needs to be reviewed and approved by the client and then Test Plan Document is signed-off by the Client
Exit Criteria:
Test Scenarios and Test Cases Documents are prepared, they need to be reviewed and signed-off by the Client
Test Execution
Entry Criteria:
Test Scenarios and Test Cases document needs to be reviewed and approved by the client and Documents are signed-off by the Client
Application is ready for Testing
Exit Criteria:
Test Case Reports, Defect Reports are ready
Test Closure
Entry Criteria:
Test Case Reports, Defect Reports are ready
Exit Criteria:
Test Summary Reports, it overviews of the entire testing process

## Slide 10: Tools:
The following are the list of Tools we will be using in this Project:
Microsoft excel sheet Tool,
word and
power point Tool

## Slide 11: Risks and Mitigations The following are the list of risks possible and the ways to mitigate them:
Risks | Mitigations
Non-Availability FRS document | Done exploratory testing
Build URL is not working in chrome alone | Used chrome alone for the entire process
Less time for Testing | Done testings on core areas given to me by conducting functional, integrations testings, exploratory testings, GUI testings.

## Slide 12: Approvals
Masai will send different types of documents for Client Approval like below:
Test Plan
Test Scenarios
Test Cases
Reports
Testing will only continue to the next steps once these approvals are done